## Area1PuzzleList
Level Number | Level Name | size | Focus | Camera Change | Mechanic 1 | Mechanic 2 | Mechanic 3 | additional info
1 | Move |  | Just moving the robot | isometric
2 | Turn |  | Turning the robot
3 | Push to box to clear path |  | Punch item | Follow directly behind
4 | Short bridge |  | Camera change/driving skill | Top down
5 | Scanner Open Gate |  | Scanner/Gate | isometric | Scanner | Gate
6 | Button Turn on Gate |  | Gate can be turn on |  | Scanner | Gate | Button
7 | Area 1 Boss |  |  | Fixed in the room | Bomb | Battery | Sawblade
Second Area(WIP)

## Production Schedule
Task Color Code | Design | Programming | Visual/Polish
Week | Date Start | Date End | Additional info | Task 1 | Task 2 | Task 3 | Task 4
1 | 2021-11-08 | 2021-11-14 |  | Refine the Control | refine the physical button | First area boss implementation? | Add Visual Feedback for Controlling the robot
2 | 2021-11-15 | 2021-11-21 |  | planning the second area | robot Arm Refine | First Area boss polish? | First Area Level polish
3 | 2021-11-22 | 2021-11-28 | Thanksgiving | planning the second area | first area with lighting/props | Starting to make necessary puzzle elements for the second area
4 | 2021-11-29 | 2021-12-05 |  | Implementing the second area | Making the second boss
5 | 2021-12-06 | 2021-12-12 | Final week? | Implementing the second area | Making the second boss
6 | 2021-12-13 | 2021-12-19 |  | Second area polish?
The goal for the end of the semester is to have the entry area feature completed and polished, second area with the level blockout and mechanics implemented.